## Hybrid Project Plan
| PROJECT NAME | STUDENT/TEAM | START DATE | END DATE |  | OVERALL PROGRESS |  |  | PROJECT DELIVERABLE | The start of a project that can be expanded upon. It will have fun, smooth movement, basic enemy AI, unique visuals made possible with shaders, lighting, and a unique artstyle.
| Cave Painting Project | Diego | 2024-04-08 | 2023-06-17 |  | 0% |  |  | SCOPE STATEMENT | 4 completed rooms to the start of a metroidvania with platforming, action, and some puzzle elements
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | HOURS | STATUS | COMMENTS
| Project Plan | Research | Diego | 50% | 2024-04-08 | 2024-06-17 | 71 | 0 | In Progress
| Tilemap design | Art |  | 0% |  |  |  |  | Complete
| Implement Enemy AI | Programming |  | 0% |  |  |  |  | In Progress
| Implement Boss AI | Programming |  | 0% |  |  |  |  | Not Started
| Implement camera movement and other smaller details | Programming |  | 0% |  |  |  |  | Not Started
| Implement lighting and shaders | Programming |  | 0% |  |  |  |  | Not Started
| Polish and test game | Research |  | 0% |  |  |  |  | Not Started
| Polish and test game | Research |  | 50% |  |  |  |  | Not Started
| Sprint 1 : Tilemap Design | Milestone |  | 0% | 2024-04-22 | 2024-04-29 | 0 | 6 | Complete
| Create map for starting area and first passageway | [6 empty] | 1 | Complete
| Create map for the first room | [6 empty] | 2 | Complete
| Create map for the second room | [6 empty] | 2 | Complete
| Create map for the boss room | [6 empty] | 1 | Complete
Not Started
| Sprint 2: Enemy AI | Milestone |  | 0% | 2024-04-29 | 2024-05-06 | 0 | 6 | Complete
| Create a way for enemies to "see" the player | "" | [5 empty] | 1 | Complete | There was a bug that I couldn't figure out for a while so it took an hour longer than expected
| Implement charging enemy | "" | [5 empty] | 3 | Complete
| Implement flying enemy | "" | [5 empty] | 2 | Complete
|  | "" | [6 empty] | Not Started
|  | "" | [6 empty] | Not Started
| Sprint 3: Boss AI | Milestone |  | 0% | 2024-05-06 | 2024-05-13 | 0 | 9 | In Progress
| Implement a generic state machine | "" | [5 empty] | 4 | Complete | Took way less time than I thought it would take (approx 1h 30)
| Create different states for the boss (3/6) | "" | [5 empty] | 2 | In Progress
| Create the transitions between those states (3/6) | "" | [5 empty] | 2 | In Progress
| Create Door class | "" | [5 empty] | 1 | Complete | The doors need to close when the boss wakes up so I had to make a reusable door class
| Create Shockwave object | "" | [5 empty] | 1 | Complete | Created a showckwave object that can be used by any enemy if they need it
| Sprint 4: Camera movement and details | Milestone |  | 0% | 2024-05-13 | 2024-05-20 | 0 | 9 | Not Started
| Find a way to change Z value of camera based on where player is on the map | Research | [5 empty] | 1 | Not Started
| Implement camera controller | "" | [5 empty] | 3 | Not Started
| Implement foreground | "" | [5 empty] | 2 | Not Started
| Implement destructible objects | "" | [5 empty] | 2 | Not Started
| Doors and door switches | "" | [5 empty] | 1 | Not Started
| Sprint 5: Lighting and Shaders | Milestone |  | 0% | 2024-05-20 | 2024-05-27 | 0 | 8 | Not Started
| Implement an ambient light that lights up most of the screen | "" | [5 empty] | 2 | Not Started
| Implement lights that are in the map | "" | [5 empty] | 2 | Not Started
| Create a shader that uses a normal map for the background | "" | [5 empty] | 4 | Not Started
|  | "" | [6 empty] | Not Started
|  | "" | [6 empty] | Not Started
| Sprint 6: Polish and Bug fixing | Milestone |  | 0% | 2024-05-27 | 2024-06-03 | 0 | 7 | Not Started
| Small flash when player gets hurt | Programming | [5 empty] | 2 | Not Started
| Screen shake on certain actions | Programming | [5 empty] | 1 | Not Started
| Test game and find features that can be improved fixed | Research | [5 empty] | 4 | Not Started
|  | "" | [6 empty] | Not Started
|  | "" | [6 empty] | Not Started
| Sprint 7: Polish and Bug fixing | Milestone |  | 50% | 2024-06-03 | 2024-06-10 | 0 | 8 | Not Started
| Test game and find features that can be improved /fixed | Research | [5 empty] | 8 | Not Started
| Be able to move spear in all directions | "" | [6 empty] | Not Started
|  | "" | [6 empty] | Not Started
|  | "" | [6 empty] | Not Started
|  | "" | [6 empty] | Not Started
| Final Project | Polishing and Preparing Presentation |  | 25% | 2024-06-10 | 2024-06-17 |  |  | Not Started
| Final Delivery | Final |  | 25% | 2024-04-22 | 2024-06-17 |  |  | Not Started
Note on A5: Mark with X to Discuss about the risks

## Data
FEATURE TYPE
Art
Programming
Documentation
Research
Animation
Sound
Project Setup
Configuration
""
Final